## Schedule
|  | Status | Owner | ETA | Comments
Candidate Info
UI Screens
UI Notification Integration
Services
| Spoc View | Completed | Murthy | 2017-08-01
| Candidate View | Completed | Murthy | 2017-08-01
| Notification Integration | Completed | Murthy | 2017-08-10 | Pending: Email subject and Body templates Replace smtp with corporate
UI - Service Integration
| E2E Testing | Not started
SPOC List View
UI Screens
UI Status Navigation
UI Notification Integration
Services
| Candidate List with Status | Completed | Murthy | 2017-08-01
| Notification Integration | Testing In-prgrss | Murthy | 2017-08-22 | Pending: Email subject and Body templates - Satish Replace smtp with corporate
UI - Service Integration
| E2E Testing | Not started
Candidate Details
UI Screens
UI Update Onboarding Info - Integration
UI Notification Integration
Services
| Candidate Details with Status and onboarding | Completed | Murthy | 2017-08-01
| Notification Integration | Testing In-prgrss | Murthy | 2017-08-22 | Pending: Email subject and Body templates - Satish Replace smtp with corporate
| UI - Service Integration | Not started
| E2E Testing | Not started
Onboarding Data
UI Screens
Services
| Add/Update data | Completed | Murthy | 2017-08-01
| UI - Service Integration | Not started
| E2E Testing | Not started
Service- Utiities
| Export Onboarding Data to Excel (POI) | Dev In-progress | Rajaneesh
| Notification Service | Completed | Murthy | 2017-08-01 | Pending: Email subject and Body templates - Satish Replace smtp with corporate
| Url Gen Service | Completed | Murthy | 2017-08-10 | Pending: To add url in Email
Admin |  | Hold
Resource - Roles
UI Screens
Services
Roles Service
UI - Service Integration
E2E Testing
Add Onboarding metadata data |  | Hold
UI Screens
Services
Metadata Service
UI - Service Integration
E2E Testing
Database setup |  | Completed | Murthy | 2017-07-20
UAT |  | Not started | Satish

## Legend
Resources |  | Status |  | Priority
| Lohitha |  | Not started |  | High
| Lohitha/Rajaneesh |  | Dev In-progress |  | Medium
| Milan |  | Testing In-prgrss |  | Low
| Murthy |  | Completed
| Murthy/Milan |  | Hold
Satish
Lohitha
Rajaneesh
Pradeep
Sreeram